## Date dd.mm.yyyy
Project acronym | [17 empty] | Review of dd.mm.yyyy
General information about the project | [17 empty] | Logo / Project illustration
Project Title:
Project Leader:
Project Description and Main Objectives
Activities / Progress since last review | [13 empty] | Project status
Total project budget:
Total Expenses (including personnel):
[14 empty] | % of budget used to date: |  |  |  |  | #DIV/0!
% overall scientific progress:
Overall status of the project (+ comments if necessary)
Activities / Problems to solve in the next few weeks | [13 empty] | Partners |  |  | Signed contracts? |  | Cash payment?
[17 empty] | Consortium agreement | Funding agreement | 1st part | 2nd part
Company name
Company name
Company name
Remarks / Others | [13 empty] | Company name
Company name
Company name
Planning & Progress (main activities) |  |  | month | month | month | month | month | month | month | month | month | month | month | month | month | month | month | month | month | month
WP0 | Kick-off dd.mm.yyyy
Intermediate report dd.mm.yyyyy
Final report dd.mm.yyyyy
WP1 | Activity
Activity
Milestone 1:
WP2
WP3
|  | Caption: |  | Initial plan: |  |  | Progress: |  | Milestones: | [6 empty] | Collaborative Project - Monthly Follow-up Sheet / PC-M-E-006.02
Information (to be deleted): possibility to use this Excel Gantt OR to copy a screenshot of your project Gantt where you can see the planning and progress of the tasks

## Example 06.10.2021
BRACO | [16 empty] | Review of 06.10.2021
General information about the project | [16 empty] | Logo / Illustration of project
Project Title: Development of a mechanical arm for watering salads
Project Leader: John Marrat
Project Description and Main Objectives
The objective of the BRACO project is to develop a mechanical arm for watering salads in greenhouses. To do this, the project is divided into 3 phases: 1. Definition of the specifications and characterization of the parts 2. Tests on pilot machines 3. Tests in real conditions at ViaB.
Activities/Progress since last review | [12 empty] | Project status
Visit of sprinkler head suppliers Study of the products on the market Specification of established metal parts | [12 empty] | Total project budget: |  |  |  |  | 150000
[13 empty] | Total Expenditures (including personnel): |  |  |  |  | 55000
[13 empty] | % of budget used to date: |  |  |  |  | 36.67%
[13 empty] | % overall scientific progress: |  |  |  |  | 35%
Overall status of the project (+ comments if necessary)
Activities / Problems to solve in the next few weeks | [12 empty] | Partners |  |  | Signed contracts? |  | Cash payment?
Visit of Blimante for the automation of the prototype Characterization of the parts in the laboratory Development of the test protocol Problem: delay in delivery of the control tablet. Search for alternatives in progress | [15 empty] | Consortium | Grant | 1st part | 2nd part
Telco
ViaB
Comu
Remarks / Others | [12 empty] | Petruniom
A Doodle invitation will be sent shortly for the organization of a workshop with the partners. | [12 empty] | Blimante
Ruit
Planning & Progress (main activities) |  | May 2021 | June 2021 | July 2021 | Aug 2021 | Sept 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | Aug 2022 | Sept 2022 | Oct 2022
WP0 | Kick-off 03.05.2021
Intermediate report 31.01.2022
Final report 30.12.2022
WP1 | Definition of specifications
Characterization of the parts
Milestone 1: technical guide
WP2 | Test phase on pilot machine
Analysis of the results
Finalization of the ABC prototype
WP3 | Tests in real conditions at ViaB
Adaptation of the prototype
Milestone 2: Finalized and validated prototype
Technology transfer
|  |  | Initial plan: |  |  | Progress: |  | Milestones: | [6 empty] | Collaborative Project - Monthly Follow-up Sheet / PC-M-E-006.02
Example for information purposes
Please delete this sheet